## l1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Search for a proper API | 2023-09-30 | 2023-10-06 | 100% | Sanjeev
2 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Implement API | 2023-09-30 | 2023-10-06 | 100% | Sanjeev
3 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Display all subscription | 2023-09-30 | 2023-10-06 | 100% | Sanjeev
4 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Implement core functionality | 2023-09-30 | 2023-10-06 | 100% | Sanjeev
5 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Implement GUI requirments | 2023-09-30 | 2023-10-06 | 100% | Bisheng & Sanjeev
6 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Implement Crosscut features | 2023-09-30 | 2023-10-06 | 100% | Bisheng & Sanjeev
6 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Develop test cases | 2023-09-30 | 2023-10-06 | 70% | Kaushal & Vaibhav
7 | 02. Search And Discovery | 2.01 | Search Hotels or Events by Text | Complete testing of test cases | 2023-09-30 | 2023-10-06 | 70% | Kaushal & Vaibhav
8 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Search for a proper API | 2023-10-07 | 2023-10-13 | 0% | Sanjeev
9 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Implement API | 2023-10-07 | 2023-10-13 | 0% | Sanjeev
10 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Display all subscription | 2023-10-07 | 2023-10-13 | 0% | Sanjeev
11 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Implement core functionality | 2023-10-07 | 2023-10-13 | 0% | Sanjeev
12 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Implement GUI requirments | 2023-10-07 | 2023-10-13 | 0% | Bisheng
13 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Implement Crosscut features | 2023-10-07 | 2023-10-13 | 0% | Sanjeev
11 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Develop test cases | 2023-10-07 | 2023-10-13 | 0% | Kaushal & Vaibhav
12 | 02. Search And Discovery | 2.02 | Apply Filters To Search Results | Complete testing of test cases | 2023-10-07 | 2023-10-13 | 0% | Kaushal & Vaibhav
13 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Search for a proper API
14 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Implement API
15 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Display all subscription
16 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Implement core functionality
17 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Implement GUI requirments
18 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Implement Crosscut features
19 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Develop test cases
20 | 03. Reviews and Ratings | 3.01 | Post Reviews And Ratings | Complete testing of test cases
21 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Search for a proper API
22 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Implement API
23 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Display all subscription
24 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Implement core functionality
25 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Implement GUI requirments
26 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Implement Crosscut features
27 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Develop test cases
28 | 03. Reviews and Ratings | 3.02 | Ability To Comment For Reviews | Complete testing of test cases
29 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Search for a proper API
30 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Implement API
31 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Display all subscription
32 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Implement core functionality
33 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Implement GUI requirments
34 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Implement Crosscut features
35 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Develop test cases
36 | 03. Reviews and Ratings | 3.03 | Ability To Upvote/Downvote Reviews | Complete testing of test cases
37 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Search for a proper API
38 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement API
39 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Display all subscription
40 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement core functionality
41 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement GUI requirments
42 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement Crosscut features
43 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Develop test cases
44 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Complete testing of test cases
45 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Search for a proper API
46 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement API
47 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Display all subscription
48 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement core functionality
49 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement GUI requirments
50 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement Crosscut features
51 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Develop test cases
52 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Complete testing of test cases
53 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Search for a proper API
54 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement API
55 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Display all subscription
56 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement core functionality
57 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement GUI requirments
58 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement Crosscut features
59 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Develop test cases
60 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Complete testing of test cases