## Road Map
Quick Feed Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/20/23 | Iteration 2 - 11/03/23 | Iteration 3 - 11/17/23 | Iteration 4 - 12/15/23
01. Account Management | 01.01 Create Account
01.02 Sign-In
01.03 Modify Account
01.04 Delete Account
01.05 View Account Details
01.06 Provide Customer Support
02. Search And Discovery | 02.01 Search Hotels or Events by Text | 5 | x |  |  |  | Features implemented in last semester
| 02.02 Apply Filters To Search Results | 4 | x
| 02.03 Suggest Keywords Related To Search | 4 | x
| 02.04 Search Hotels or Events by Photo | 4 |  |  | x
03. Reviews and Ratings | 03.01 Post Reviews And Ratings | 5 |  | x
| 03.02 Ability To Comment For Reviews | 4 |  | x
| 03.03 Ability To Upvote/Downvote Reviews | 4 |  | x
04. Suggestions And Recommendations | 04.01 Recommend Hotels Or Event Based On Usage | 5 |  |  | x
| 04.02 View Usage Pattern | 4 |  |  |  | x
| 04.03 Modify Suggestion Patterns | 4 |  |  |  | x
|  | VELOCITY: | 13 | 13 | 9 | 8
v

## Story Map
Epics |  | QuickFeed - User Story Map
Epic 1 - Account Management |  | Epic 1 - Account Management | Epic 2 - Search And Discovery | Epic 3 -Reviews and Ratings | Epic 4 - Suggestions And Recommendations
Epic 2 - Search And Discovery |  |  | 02.01 Search Hotels or Events by Text
Epic 3 - Reviews and Ratings |  |  | 02.02 Apply Filters To Search Results |  |  | Iteration 1
Epic 4 - Suggestions And Recommendations | User Stories |  | 02.03 Suggest Keywords Related To Search
03.01 Post Reviews And Ratings
03.02 Ability To Comment For Reviews
|  |  |  | 03.03 Ability To Upvote/Downvote Reviews |  | Iteration 2
02.04 Search Hotels or Events by Photo
[5 empty] | 04.01 Recommend Hotels Or Event Based On Usage | Iteration 3
[5 empty] | 04.02 View Usage Pattern | Iteration 4
04.03 Modify Suggestion Patterns