## Initial Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2023 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[6 empty] | Date | 2023-01-24 | 2023-01-31 | 2023-02-07 | 2023-02-14 | 2023-02-21 | 2023-02-28 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
Project Phase |  | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | All | 2023-01-24 | 2023-01-26 | 100%
| Confirm Project Team Roles |  | All | 2023-01-24 | 2023-01-26 | 100%
| Develop two business cases |  | All | 2023-01-24 | 2023-01-29 | 100%
| Develop Project Initiation Document (PID) |  | All | 2023-01-31 | 2023-02-05 | 100%
| Produce initial Project Plan, RACI |  | Sanjeev Kumar | 2023-02-07 | 2023-02-12 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Bisheng, Vaibhav | 2023-02-14 | 2023-02-19 | 100%
| Produce Context Diagram, Define System Interfaces |  | Sai Kiran, Prasad, Sanjeev | 2023-02-14 | 2023-02-19 | 100%
| Define Business Requirements |  | Nayan Yadav | 2023-02-14 | 2023-02-19 | 100%
| Agree to System Requirements types |  | All | 2023-02-14 | 2023-02-19 | 100%
| Produce Home Page Structure Document |  | Bisheng | 2023-02-21 | 2023-02-26 | 100%
| Produce Business Requirements Diagram |  | All | 2023-02-21 | 2023-02-26 | 100%
| Define Functional Decomposition & Fishbone Diagram |  | All | 2023-02-21 | 2023-02-26 | 100%
| Produce RCT document |  | All | 2023-02-21 | 2023-02-26 | 100%
| Decide which features to implement this semester |  | All | 2023-02-28 | 2023-03-05 | 100%
| Produce analysis diagrams (UML, DFD) |  | All | 2023-02-28 | 2023-03-05 | 100%
| Define functional requirements (User Stories) |  | All | 2023-02-28 | 2023-03-05 | 100%
| Update Project Plan with additional requirements tasks |  | Sanjeev Kumar | 2023-02-28 | 2023-03-05 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Sanjeev | 2023-04-04 | 2023-04-09 | 0%
| Database Design (ERD, Table spec) |  | All | 2023-03-21 | 2023-03-26 | 0%
| Data-flow Diagram (physical) |  | Prasad | 2023-03-21 | 2023-03-26 | 0%
| User interface design |  | Bisheng, Sanjeev | 2023-02-14 | 2023-04-10 | 0%
MILESTONE 3: DESIGN COMPLETED
Coding | Create Account | GUI & Functionality Detailed Design | Sanjeev, Bisheng | 2023-02-14 | 2023-03-07 | 100%
|  | Coding & Implemenation | Sanjeev, Bisheng | 2023-02-28 | 2023-03-07 | 100%
| Sign In | GUI & Functionality Detailed Design | Sanjeev, Bisheng | 2023-02-14 | 2023-03-07 | 100%
|  | Coding & Implemenation | Sanjeev, Bisheng | 2023-02-28 | 2023-03-07 | 100%
| Modify Account | GUI & Functionality Detailed Design | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 50%
|  | Coding & Implemenation | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 50%
| Delete Account | GUI & Functionality Detailed Design | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 50%
|  | Coding & Implemenation | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 50%
| View Account Details | GUI & Functionality Detailed Design | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 0%
|  | Coding & Implemenation | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 0%
| Provide Customer Support | GUI & Functionality Detailed Design | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 0%
|  | Coding & Implemenation | Sanjeev, Bisheng | 2023-04-18 | 2023-04-23 | 0%
| Implement Coding for CrossCuts | Field Validation | Sanjeev | 2023-04-04 | 2023-04-10 | 100%
|  | Connectivity | Sanjeev, Bisheng | 2023-04-04 | 2023-04-10 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
| Evaluate Features to be Tested |  | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
| Create Account | Design Test case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Execute Test Case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Analyze Test Result | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
| Sign In | Design Test case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Execute Test Case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Analyze Test Result | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
| Modify Account | Design Test case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Execute Test Case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Analyze Test Result | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
| Delete Account | Design Test case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Execute Test Case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
|  | Analyze Test Result | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 50%
| View Account Details | Design Test case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 0%
|  | Execute Test Case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 0%
|  | Analyze Test Result | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 0%
| Provide Customer Support | Design Test case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 0%
|  | Execute Test Case | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 0%
|  | Analyze Test Result | Kaushal, Vignan, Vaibhav | 2023-04-18 | 2018-04-23 | 0%
| Implement Testing for CrossCuts | Field Validation | Kaushal, Vignan, Vaibhav | 2023-04-04 | 2023-04-10 | 50%
|  | Connectivity | Kaushal, Vignan, Vaibhav | 2023-04-04 | 2023-04-10 | 50%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2023-05-02 | 2023-05-09 | 0%