## l3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Search for a proper API | 2023-11-04 | 2023-11-09 | 100% | Sanjeev
2 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Implement API | 2023-11-04 | 2023-11-09 | 100% | Sanjeev
3 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Create database tables | 2023-11-04 | 2023-11-09 | 100% | Sanjeev
4 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Implement core functionality | 2023-11-04 | 2023-11-09 | 100% | Sanjeev
5 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Implement GUI requirments | 2023-11-04 | 2023-11-09 | 100% | Sanjeev
6 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Develop test cases | 2023-11-04 | 2023-11-09 | 100% | Kaushal & Vaibhav
7 | 02. Search And Discovery | 2.03 | Suggest Keywords Related To Search | Complete testing of test cases | 2023-11-04 | 2023-11-09 | 100% | Kaushal & Vaibhav
8 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Search for a proper API | 2023-11-11 | 2023-11-16 | 100% | Sanjeev
9 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement API | 2023-11-11 | 2023-11-16 | 100% | Sanjeev
10 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Create database tables | 2023-11-11 | 2023-11-16 | 100% | Sanjeev
11 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement core functionality | 2023-11-11 | 2023-11-16 | 100% | Sanjeev
12 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Implement GUI requirments | 2023-11-11 | 2023-11-16 | 100% | Sanjeev
13 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Develop test cases | 2023-11-11 | 2023-11-16 | 100% | Kaushal & Vaibhav
14 | 04. Suggestions And Recommendations | 4.01 | Recommend Hotels Or Event Based On Usage | Complete testing of test cases | 2023-11-11 | 2023-11-16 | 100% | Kaushal & Vaibhav

## l4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Search for a proper API | 2023-11-25 | 2023-11-29 | 100% | Sanjeev
2 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement API | 2023-11-25 | 2023-11-29 | 100% | Sanjeev
3 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Create database tables | 2023-11-25 | 2023-11-29 | 100% | Sanjeev
4 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement core functionality | 2023-11-25 | 2023-11-29 | 100% | Sanjeev
5 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Implement GUI requirments | 2023-11-25 | 2023-11-29 | 100% | Sanjeev
6 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Develop test cases | 2023-11-25 | 2023-11-29 | 100% | Kaushal & Vaibhav
7 | 04. Suggestions And Recommendations | 4.02 | View Usage Pattern | Complete testing of test cases | 2023-11-25 | 2023-11-29 | 100% | Kaushal & Vaibhav
8 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Search for a proper API | 2023-12-09 | 2023-12-14 | 100% | Sanjeev
9 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement API | 2023-12-09 | 2023-12-14 | 100% | Sanjeev
10 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Create database tables | 2023-12-09 | 2023-12-14 | 100% | Sanjeev
11 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement core functionality | 2023-12-09 | 2023-12-14 | 100% | Sanjeev
12 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Implement GUI requirments | 2023-12-09 | 2023-12-14 | 100% | Sanjeev
13 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Develop test cases | 2023-12-09 | 2023-12-14 | 100% | Kaushal & Vaibhav
14 | 04. Suggestions And Recommendations | 4.03 | Modify Suggestion Patterns | Complete testing of test cases | 2023-12-09 | 2023-12-14 | 100% | Kaushal & Vaibhav